## Project schedule
SD (Systems Development) Group Project | [8 empty] | Project Start: | [6 empty] | 2025-11-23 | [11 empty] | Project End: | [7 empty] | 2026-04-01
Project Management & Task Assignment | [8 empty] | Display week: | [6 empty] | -1
Hasaan (Project Manager), Rayyan (Technical Lead), Royden (UI/UX Lead), Ishaq (Data Engineer)
[9 empty] | 2025-11-10 | [5 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04
OBJECTIVE | OBJ DESC | ASSIGNED TO | PROGRESS | START | END | REQUIREMENT | TASK | time axis 2025-11-10 to 2026-05-08
 | time axis 2025-11-10 to 2026-05-08
Objective 1: Data Ingestion & Preprocessing | Develop robust data ingestion module to read, validate, and preprocess CSV sales data | Ishaq | 0% | 2025-11-08 | 2025-11-15 | FR1 Read Sales CSV Data | Upload CSV file Function | 8
|  | Ishaq | 100% | 2025-11-03 | 2025-11-07 |  | Read CSV file
|  | Ishaq | 100% | 2025-11-03 | 2025-11-07 |  | Clean data using Pandas | 5
|  | Ishaq | 0% | 2025-11-03 | 2025-11-10 | FR1- Read Sales CSV Data & NFR4 - Reliability | Error handling for data quality (missing values, duplicates) | 8
Objective 2: Historical Data Visualization | Design and implement interactive dashboard displaying historical sales trends for top 6 products | Rayyan |  |  |  | FR2 | Dashboard displaying historical sales trends for the top 3 food items and top 3 coffee products
|  | Royden |  |  |  | FR3 | Dashboard displays 6 distinct charts showing 4+ weeks of sales data with clear axes
|  | Rayyan |  |  |  |  | Implement product ranking logic (FR2)
|  | Royden |  |  |  |  | System MUST display historical sales fluctuations using line charts
|  | Royden, Rayyan |  |  |  | NFR6 & NFR5 | Apply Bristol-Pink color scheme
|  | Royden, Rayyan |  |  |  | NFR3 & NFR5 | Design dashboard mockup/wireframes
Objective 3: Predictive Model Development | Select, train, and evaluate suitable ML/time-series algorithm to forecast 4-week sales | ALL |  |  |  | FR4 - Sales Prediction | Select ML/time-series algorithm - Research ARIMA/Prophet/LSTM
|  | Hasaan |  |  |  |  | Implement prediction model - training
|  | Hasaan |  |  |  |  | Implement 28-day forecast generation
|  | Hasaan |  |  |  |  | Display predictions - table and chart (FR5)
|  | Hasaan |  |  |  | NFR1- Performance NFR2 - Accuracy | Calculate and display MAPE (Mean Absolute % Error)
|  | Hasaan |  |  |  |  | Model validation testing, test on hold-out dataset
|  | Hasaan, Royden |  |  |  |  | Display MAPE and accuracy metrics in dashboard section
Objective 4: Interactive Prediction Interface | Implement user-interactive features for training period selection, zoom, and predictions vs actuals | Ishaq, Rayyan |  |  |  | FR4 - Sales Predictions | Implement zoom/date range filter
|  | Hasaan, Royden |  |  |  |  | Implement training period selector - slider widget
|  | Hasaan, Royden |  |  |  |  | Implement comparison view - overlay charts
|  | Ishaq, Rayyan |  |  |  | FR4 - Sales Predictions & NFR7 - Security | Implement user authentication - password hashing
|  | ALL |  |  |  | FR4 - Sales Predictions | Finalise interactive features (Milesone) - demo to mentor
Objective 5: Testing, Documentation & Deployment | Conduct comprehensive testing, complete documentation, prepare final demonstration | ALL |  |  |  | NFR1 | Performance testing - measure load time
|  | ALL |  |  |  | NFR3, NFR4, & NFR5 | Usability testing - 2+ participants, 5 min tasks
|  | ALL |  |  |  | All functional requirements | System testing - all requirements
|  | ALL |  |  |  | - | Code documentation - comments & README
|  | ALL |  |  |  | - | Write full report sections (Introduction, Literature, Design, Implementation, Testing, Evaluation)
|  | ALL |  |  |  | - | Each member: Individual reflective essay on group work, learning, skills

## Requirements
ID | Requirement | SMART Description | Acceptance Criteria | MoSCoW | Source
FR1 | Read Sales CSV Data | System must allow user to upload and process sales data CSV file within 5 seconds; errors shown in UI by Week 3. | File upload, errors handled, DataFrame created in <5s across 3 tests. | Must
FR2 | Display Top 3 Products | System must show most-sold Croissant (1 class) & Coffee (2 classes) in chart, auto-updating for last 4 weeks, by Week 5. | Correct bar/line chart; validated against dataset. | Must
FR3 | Sales Fluctuation Graph | System provides selectable line graph of sales fluctuation for 6 items; user can set 4-week window by end of Week 6. | Graph updates when user changes date window; matches data. | Must
FR4 | Sales Prediction | At least one ML model (Prophet/ARIMA) predicts next 28 days for any chosen product on dashboard by Week 8. | Table/plot of predictions shown, MAPE <35% on test set. | Must
FR5 | Adjust Training Window | User can select training period (4-8 weeks) in dashboard, affecting model results live by Week 10. | Slider/dropdown changes training window, output/metrics update. | Should
FR6 | Export Predictions | User can export predictions/historical data to CSV file from dashboard by Week 12. | 'Export' button downloads CSV; tested on Chrome/Edge. | Should
ID | Requirement | SMART Description | Acceptance Criteria | MoSCoW | Source
NFR1 | Performance | All dashboard actions (load/process/display) complete in <5 seconds, confirmed in final testing. | 90% of actions on mid-range laptop <5s in test report. | Must
NFR2 | Accuracy | Predictions must achieve Mean Absolute Percentage Error (MAPE) ≤ 35% on test data by Week 12. | MAPE script and dashboard values ≤35% on test holdout. | Must
NFR3 | Usability | UI/UX rated good (≥4/5) by 3+ peers/mentor in Week 14 review with labeled controls. | Feedback form; all controls labeled; ≥4/5 score. | Must
NFR4 | Reliability | System handles missing/corrupt files and informs user via error message; never crashes in 5 error test cases by Week 14. | Errors in 5 file tests handled with UI message, no crash. | Must
NFR5 | Responsiveness | Dashboard renders correctly and maintains usability on desktop, tablet, mobile at 3 tested resolutions by Week 14. | Usable on 3+ device types, confirmed by peers. | Should
NFR6 | Accessibility | Dashboard color scheme (black/pink/white) and text pass WCAG AA contrast; resizes to 150% in Chrome. | Accessibility/contrast test logs attached in report. | Should
NFR7 | Security | Implement user authentication (passwords) and manage in database logs with correct keying. | User details hashed and login session managed | Should

## Objectives
OBJECTIVES (SMART) | OBJECTIVE NAME | VERIFICATION METHOD
Objective 1 | DATA INGESTION AND PREPROCESSING
Objective 1 - Specific | Develop a robust data ingestion module that reads, validates, and preprocesses CSV sales data files containing historical transaction records | Verification: Successful loading of test CSV; error logs for invalid data; mentor code review
Objective 1 - Measurable | Successfully load sample CSV files (min. 4 weeks of data) with error handling for missing/malformed data; demonstrate with test dataset by Week 3 | Verification: Unit tests pass; sample data processed without errors
Objective 1 - Achievable | Use Python with Pandas library; team has existing Python knowledge; CSV format is standardized | Verification: Team skills assessment; library documentation reviewed
Objective 1 - Relevant | Essential foundation for all analysis and prediction tasks; directly addresses requirement to process historical sales data | Verification: Linked to Requirements FR1, FR2 in Requirements sheet
Objective 1 - Time-bound | Complete and demonstrate to mentor by Week 3 (Nov 10, 2025) | Verification: Gantt chart milestone; GitHub commit by deadline
Objective 2 | HISTORICAL DATA VISUALIZATION
Objective 2 - Specific | Design and implement an interactive dashboard displaying historical sales trends for the food items and top coffee products (of the 2 available) using appropriate graphical representations | Verification: Dashboard renders all 6 charts; peer review feedback form completed
Objective 2 - Measurable | Dashboard displays 6 distinct charts showing 4+ weeks of sales data with clear axes, legends, and labels; peer review confirms clarity by Week 5 | Verification: UI checklist confirms all elements present; mentor sign-off
Objective 2 - Achievable | Use Streamlit/Plotly libraries; similar dashboards completed in previous modules; design templates available | Verification: ASD Gantt chart shows completed similar work; Streamlit tutorials reviewed
Objective 2 - Relevant | Provides stakeholders with visual insights into sales patterns; required deliverable per case study specifications | Verification: Case study explicitly requests graphical display of top products
Objective 2 - Time-bound | Complete dashboard prototype by Week 5 (Nov 24, 2025); finalize by Week 8 | Verification: Formative feedback session scheduled Week 5; final review Week 8
Objective 3 | PREDICTIVE MODEL DEVELOPMENT
Objective 3 - Specific | Select, train, and evaluate at least one suitable time-series or machine learning algorithm to forecast 4-week sales volumes for key products | Verification: Model evaluation script outputs MAPE; prediction CSV generated for 28 days
Objective 3 - Measurable | Model generates 28-day predictions with Mean Absolute Percentage Error (MAPE) < 10%; model evaluation report documents performance by Week 10 | Verification: MAPE calculation documented in notebook; threshold < 10% confirmed
Objective 3 - Achievable | Team will research ARIMA, Prophet, or LSTM models via literature review; Scikit-learn/statsmodels libraries available; similar models covered in ML modules | Verification: Literature review cites 3+ relevant papers; model comparison table completed
Objective 3 - Relevant | Core technical requirement; predictive accuracy directly impacts inventory optimization and waste reduction goal | Verification: Risk register identifies prediction accuracy as critical success factor
Objective 3 - Time-bound | Initial model training by Week 7 (Dec 8, 2025); achieve MAPE target by Week 10 (Jan 5, 2026) | Verification: Testing phase begins Week 7; performance report due Week 10
Objective 4 | INTERACTIVE PREDICTION INTERFACE
Objective 4 - Specific | Implement user-interactive features allowing selection of training period (4-8 weeks), zoom functionality for date ranges, and graphical comparison of predictions vs. actuals | Verification: Screen recording shows all interactive features functioning; mentor test session
Objective 4 - Measurable | Users can adjust training period via slider/dropdown; zoom feature allows date selection; comparison view displays overlayed charts; demonstrated to mentor by Week 11 | Verification: Feature checklist confirms slider, zoom, comparison view all operational
Objective 4 - Achievable | Streamlit supports interactive widgets; team member with UI/UX interest assigned; similar features implemented in ASD module | Verification: Team member CVs show relevant skills; ASD module completion referenced
Objective 4 - Relevant | Enhances usability and allows stakeholders to test different forecasting scenarios; addresses requirement for interactive dashboard | Verification: Requirements FR6, FR7, FR8 addressed; enhances user engagement
Objective 4 - Time-bound | Complete feature implementation by Week 11 (Jan 12, 2026); user testing by Week 12 | Verification: User testing session with 2+ external participants; feedback documented
Objective 5 | TESTING, DOCUMENTATION, AND DEPLOYMENT
Objective 5 - Specific | Conduct comprehensive system testing against test plan, complete technical documentation, and prepare final demonstration with critical evaluation | Verification: Test plan document with pass/fail results; word count verified; demonstration timing checked
Objective 5 - Measurable | Test plan covers all functional/non-functional requirements; documentation includes user guide and technical report (6000 words max); 18-min demonstration delivered; all measured via rubric criteria | Verification: Assessment rubric confirms all criteria met; Turnitin submission successful
Objective 5 - Achievable | Testing methodologies covered in module; documentation templates provided; adequate time allocated for refinement based on formative feedback | Verification: Test plan reviewed by mentor; formative feedback incorporated; rehearsal conducted
Objective 5 - Relevant | Ensures system quality and completeness; required for assessment submission and professional presentation of work | Verification: Module assessment brief criteria checked; portfolio contents validated
Objective 5 - Time-bound | Testing: Weeks 12-13 (Jan-Feb 2026); Documentation: Weeks 13-14 (Feb 2026); Final submission by April 2, 2026 | Verification: Submission checklist completed; all deliverables uploaded to Blackboard
AIM: | The aim of this project is to design, implement, and evaluate an intelligent forecasting dashboard that supports Bristol Pink Café managers in decision-making by reducing food waste and optimising inventory purchases using advanced data analytics and machine learning, delivered as a deployable system by the end of the project timeline.
DESIGN PHASE:
UML Diagrams
UI / UX Diagrams
Database Design
Pseudocode / Algorithm